## Slide 1: Project Management & Information Technology
Information Technology Project Management, Seventh Edition
Chapter 2

## Slide 2: Learning Objectives
Describe the systems view of project management and how it applies to information technology (IT) projects
Understand organizations, including the four frames, organizational structures, and organizational culture
Explain why stakeholder management and top management commitment are critical for a project’s success

## Slide 3: Learning Objectives
Understand the concept of a project phase and the project life cycle, and distinguish between project development and product development
Discuss the unique attributes and diverse nature of IT projects
Describe recent trends affecting IT project management, including globalization, outsourcing, virtual teams, and agile project management

## Slide 4: Projects Cannot Be Run In Isolation
Projects must operate in a broad organizational environment
Project managers need to use systems thinking
Senior managers must make sure projects continue to support current business needs

## Slide 5: A Systems View of Project Management
A systems approach emerged in the 1950s to describe a more analytical approach to management and problem solving
Includes:
  Systems philosophy
  Systems analysis
  Systems management

## Slide 6: Three Sphere Model for Systems Management

## Slide 7: Perspectives on Organizations

## Slide 8: What Went Wrong?
In a paper titled “A Study in Project Failure,” two researchers examined the success and failure of 214 IT projects over an eight-year period in several European countries.
The researchers found that only one in eight (12.5 percent) were considered successful in terms of meeting scope, time, and cost goals.
The authors said that the culture within many organizations is often to blame
Among other things, people often do not discuss important leadership, stakeholder, and risk management issues

## Slide 9: Factors Influencing IT Project Management
Organizational Structure
Organizational Culture
Top Management Commitment
Stakeholder Management
Commitment to IT
IT Governance/Organizational Standards

## Slide 10: Organizational Structures
3 basic organization structures
  Functional
  Project
  Matrix

## Slide 11: Organizational Structure Influences on Projects

## Slide 12: Organizational Culture
Organizational culture is a set of shared assumptions, values, and behaviors that characterize the functioning of an organization
Characteristics of Org. Culture
Member identity*
Group emphasis*
People focus
Unit integration*
Control
Risk tolerance*
Reward criteria*
Conflict tolerance*
Means-ends orientation
Open-systems focus*

## Slide 13: Top Management Commitment
People in top management positions are key stakeholders in projects
A very important factor in helping project managers successfully lead projects is the level of commitment and support they receive from top management
How does Top Management help a project?

## Slide 14: Stakeholder Management
Project managers must take time to identify, understand, and manage relationships with all project stakeholders
Using the four frames of organizations can help meet stakeholder needs and expectations
Who is often considered one of the most important stakeholders?

## Slide 15: Organizational Commitment to IT
If the organization has a negative attitude toward IT, it will be difficult for an IT project to succeed
Having a Chief Information Officer (CIO) at a high level in the organization helps IT projects
Assigning non-IT people to IT projects also encourage more commitment

## Slide 16: IT Governance / Standards
IT governance addresses the authority and control for key IT activities in organizations, including IT infrastructure, IT use, and project management
Standards
  PMO or simply having templates/forms
  Example: Texas Tech IT PM Standards

## Slide 17: Project Phases and the Project Life Cycle
A project life cycle is a collection of project phases that defines
  what work will be performed in each phase
  what deliverables will be produced and when
  who is involved in each phase, and
  how management will control and approve work produced in each phase
A deliverable is a product or service produced or provided as part of a project

## Slide 18: Phases of the Traditional Project Life Cycle

## Slide 19: Product Life Cycles
The Systems Development Life Cycle (SDLC) is a framework for describing the phases involved in developing and maintaining information systems
Systems development projects can follow
  Predictive life cycle
  Adaptive Software Development (ASD) life cycle

## Slide 20: Examples of Predictive Life Cycle Models
Waterfall model
Spiral model
Incremental build model
Prototyping model
Rapid Application Development (RAD) model

## Slide 21: Agile Software Development
Agile software development has become popular to describe new approaches that focus on close collaboration between programming teams and business experts

## Slide 22: The Importance of Project Phases and Management Reviews
A project should successfully pass through each of the project phases in order to continue on to the next
Management reviews, also called phase exits or kill points, should occur after each phase to evaluate the project’s progress, likely success, and continued compatibility with organizational goals

## Slide 23: What Went Right?
"The real improvement that I saw was in our ability toin the words of Thomas Edisonknow when to stop beating a dead horse.…Edison's key to success was that he failed fairly often; but as he said, he could recognize a dead horse before it started to smell...In information technology we ride dead horsesfailing projectsa long time before we give up. But what we are seeing now is that we are able to get off them; able to reduce cost overrun and time overrun. That's where the major impact came on the success rate.”*
Many organizations, like Huntington Bancshares, Inc., use an executive steering committee to help keep projects on track.
*Cabanis, Jeannette, "'A Major Impact': The Standish Group's Jim Johnson On Project Management and IT Project Success," PM Network, PMI, Sep.1998, p. 7

## Slide 24: The Context of IT Projects
Diverse in terms of size, complexity, products produced, application area, and resource requirements
Diverse IT Project Team Members
Diverse Technologies

## Slide 25: Article: Tech Project and Direction
What have they been doing due to the recession and what direction are the moving into?
What are some of the top projects?
What industries are seeing growth in major IT projects?

## Slide 26: Article: Project Management & Software Development
Software development projects have distinct characteristics not found in other projects
Based on the article, what are some of these characteristics?
Which did you feel was the number one mistake a PM could do in software development projects?

## Slide 27: Closer to home….State Projects
Were state IT projects considered to be successful?
What were some of the main issues with state IT projects?
What are the recommendations for the review board?
  Do you feel these are sufficient to fix the issues?

## Slide 28: Improving Likelihood of Success for IT Projects
Value-Driven Approach
Socio-Technical Approach
Commit to Project Management Principles (Chaos Report)
Knowledge-Management Approach

## Slide 29: Recent Trends Affecting IT Project Management
Globalization
Outsourcing
Virtual teams

## Slide 30: Important Issues and Suggestions Related to Globalization
Issues
  Communications
  Trust
  Common work practices
  Tools
Suggestions
  Employ greater project discipline
  Think global but act local
  Keep project momentum going
  Use newer tools and technology

## Slide 31: Outsourcing
Organizations remain competitive by using outsourcing to their advantage, such as finding ways to reduce costs
Their next challenge is to make strategic IT investments with outsourcing by improving their enterprise architecture to ensure that IT infrastructure and business processes are integrated and standardized

## Slide 32: Virtual Teams: Advantages/Disadvantages
Advantages:
  Increasing competiveness and responsiveness
  Lowering costs
  Increased expertise and flexibility
  Increased work/life balance
Disadvantages:
  Isolation &Interpersonal Relationships
  Communication Problems
  Dependence on Technology

## Slide 33: Approaches and Philosophy
eXtreme Project Management (XPM)
  Holistic veiw of planning and managing
  Projects don’t always fit traditional scheduling and formal techniques (they are chaotic)
  Focuses on the “human side” of PM
Agile Project Management
  Iterative, incremental approach
  Popular
    http://www.pmi.org/Certification/New-PMI-Agile-Certification.aspx

## Slide 34: Discussion
Given our past two lectures, do you feel it is harder to manage an IT project compared to a traditional project?
Name a few approaches you would use to manage stakeholders.

## Slide 35: Chapter Summary
Systems approach when working on projects
Organization frames: structural, human resources, political, and symbolic
Project managers need to consider several factors due to the unique context of information technology projects
Recent trends affecting IT project management include globalization, outsourcing, virtual teams, and Agile