## Slide 1: Agile Approach: Case Study
Information Technology Project Management, Seventh Edition
Chapter 3

## Slide 2: Project Management Process Groups
Project management process groups include
  initiating processes
  planning processes
  executing processes
  monitoring and controlling processes
  closing processes

## Slide 3: Process Groups & Knowledge Areas
Process groups vs. knowledge areas
Knowledge areas cross the various process groups including some key distinctions

## Slide 4: Project Management Process Groups and Knowledge Area Mapping*

## Slide 5: Global Issues – India and Agile
A 2011 study of organizations across India included the following findings:
  Agile Adoption Increasing
  Significant Cultural shift for Agile
  Paired Programming and Open Workspace are not popular

## Slide 6: An Informed Decision
It is not a snap decision whether to use an agile approach or not, just like flying or driving somewhere on a trip
The approach has to fit the culture, project, etc. at the organization to be successful.

## Slide 7: PM Network: A Philosophical Makeover
Impact of Agile PM
Challenges of starting Agile
Best Practice?
Support

## Slide 8: PM Network: The Sweet Spot
Beyond Software Development
Is it the right fit?

## Slide 9: Agile Approach: JWD Consulting’s Project Management Intranet Site
An agile project team typically uses several iterations or deliveries of software instead of waiting until the end of the project to provide one product.

## Slide 10: Traditional Approach: JWD Project Management Intranet Site
Pre-Initiation
  Generate Business Case (includes high level estimates on scope, cost, time, etc.)
  Identify Sponsor and PM
Initiation
  Project Charter
  Stakeholder Identification

## Slide 11: Traditional Approach: JWD Project Management Intranet Site
Planning
  Team Contract
  Scope Statement
  WBS
  Gantt chart
  Risks
Execution
  PM acquires team then directs and manages work
    Milestone reporting
  Update progress (handle human resource issues)
  Manage Communications
  Ensure stakeholders remain engaged

## Slide 12: Traditional Approach: JWD Project Management Intranet Site
Monitor and Controlling
  Change Control
  Validate/Control Scope
  Scheduling (forecasts)
  Progress Reports
Closing
  Final report and presentation
  Client sign-off
  Lessons-learned

## Slide 13: Scrum Roles & Artifacts
Scrum Roles
  Product owner
  ScrumMaster
  Scrum team or development team
Artifacts
  Product backlog
  Sprint backlog
  Burndown chart

## Slide 14: Scrum Ceremonies
Sprint planning session
Daily Scrum
Sprint reviews
Sprint retrospectives

## Slide 15: Scrum Framework and the Process Groups

## Slide 16: Unique Scrum Activities by Process Group

## Slide 17: Pre-Initiation and Initiation
Pre-Initiation and Initiation major tasks
  # of releases and functionality by release
  Sprints in release
  Charter
  Stakeholder Register
  Kick-off Meetings

## Slide 18: Planning
Similar to Traditional Process Groups
Differences

## Slide 19: JWD Intranet Site Project Baseline Gantt Chart Using Scrum Approach
3 releases vs.
1 release

## Slide 20: JWD Product and Sprint Backlogs

## Slide 21: Executing
Similarities to Traditional Process Groups
Differences

## Slide 22: Monitoring and Controlling
Similarities to Traditional Process Groups
Differences

## Slide 23: Figure 3-7. Burndown Chart

## Slide 24: Closing
Similarities to Traditional Process Groups
Differences:

## Slide 25: Chapter Summary
Project Management Process Groups
Main activities of each process group mapped to knowledge areas
Information technology project management methodologies
JWD Consulting – Predictive vs. Agile
  Biggest Difference: providing three releases of useable software versus just one