## Slide 1: Human Resource Management
PMI Knowledge Areas

## Slide 2: The Importance of Human Resource Management
Many corporate executives have said, “People are our most important asset”
People determine the success and failure of organizations and projects

## Slide 3: The Global IT Workforce
Although there have been ups and downs in the IT labor market, there will always be a need for good IT workers
  The Digital Planet 2010 study predicts that ICT spending will have an annual growth rate of more than 6 percent each year through 2013, when it will reach almost $5 trillion
Thirty-three percent of the world’s population is online, and 45 percent of Internet users are below the age of 25

## Slide 4: What is Project Human Resource Management?
Making the most effective use of the people involved with a project
Processes include
  Plan human resource management (Planning)
  Acquiring the project team (Executing)
  Developing the project team (Executing)
  Managing the project team (Control/Monitor)

## Slide 5: Figure 9-1. Project Human Resource Management Summary

## Slide 6: Keys to Managing People
Psychologists and management theorists have devoted much research and thought to the field of managing people at work
Important areas related to project management include:
  motivation theories
  influence and power
  effectiveness

## Slide 7: Ways to Influence that Help and Hurt Projects
Projects are more likely to succeed when project managers influence with
Projects are more likely to fail when project managers rely too heavily on

## Slide 8: Power
Power is the potential ability to influence behavior to get people to do things they would not otherwise do
Types of power

## Slide 9: Planning Process Group: Developing the Human Resource Plan
Used to determine the roles that will perform schedule activities and to develop the staff management plan to fill the roles with team members
Contents include
  project organizational charts
  staffing management plan
  responsibility assignment matrixes
  resource histograms

## Slide 10: Inputs: Enterprise Environmental Factors
How do different departments and the people within the performing organization interact with each other?
Enterprise Environmental Factors to consider

## Slide 11: Sample Organizational Chart for a Large IT Project

## Slide 12: Work Definition and Assignment Process

## Slide 13: Responsibility Assignment Matrices
A responsibility assignment matrix (RAM) is a matrix that maps the work of the project as described in the WBS to the people responsible for performing the work as described in the OBS

## Slide 14: Sample RACI Chart
R = responsibility
A = accountability, only one A per task
C = consultation
I = informed

## Slide 15: Staffing Management Plans and Resource Histograms
A staffing management plan describes when and how people will be added to and taken off the project team
A resource histogram is a column chart that shows the number of resources assigned to a project over time

## Slide 16: Planning Process Group: Acquiring the Project Team
Acquiring qualified people for teams is crucial
It’s important to assign the appropriate type and number of people to work on projects at the appropriate times

## Slide 17: Inputs into Acquiring Team
Human Resource Plan
Enterprise Environmental Factors
  Availability
  Competency
  Experience
  Interests
  Cost

## Slide 18: Resource Assignment
Staffing plans and good hiring procedures are important, as are incentives for recruiting and retention
Do your homework
What happens when you don’t?

## Slide 19: Be Aware of Resource Loading
Resource loading
  Helps project managers develop a general understanding of the demands a project will make on the organization’s resources and individual people’s schedules
Overallocation

## Slide 20: Resource Leveling
Resource leveling is a technique for resolving resource conflicts by delaying tasks

## Slide 21: Benefits of Resource Leveling
When resources are used on a more constant basis, they require less management
It may enable project managers to use a just-in-time inventory type of policy for using subcontractors or other expensive resources
It results in fewer problems for project personnel and accounting department
It often improves morale

## Slide 22: Planning Process Group: Developing the Project Team
The main goal of team development is to help people work together more effectively to improve project performance
Team Development (progressive stages)

## Slide 23: Developing the Project Team

## Slide 24: DISC Profiles
Also uses a four-dimensional model of normal behavior
  Dominance
  Influence
  Steadiness
  Compliance
People in opposite quadrants can have problems understanding each other

## Slide 25: Figure 9-10. The DISC Profile

## Slide 26: Reward and Recognition Systems
Team-based reward and recognition systems can promote teamwork
Focus on rewarding teams for achieving specific goals
Allow time for team members to mentor and help each other to meet project goals and develop human resources

## Slide 27: Control/Monitoring Process Group: Managing the Project Team
Project managers must lead their teams in performing various project activities
After assessing team performance and related information, the project manager must decide:
  if changes should be requested to the project
  if corrective or preventive actions should be recommended
  if updates are needed to the project management plan or organizational process assets.

## Slide 28: Conflict Handling Modes
Confrontation
Compromise
Smoothing
Forcing
Withdrawal
Collaborating
http://www.youtube.com/watch?v=6xCkhV7zhuw

## Slide 29: Conflict Can Be Good
Conflict often produces important results, such as new ideas, better alternatives, and motivation to work harder and more collaboratively
Research suggests that task-related conflict often improves team performance, but emotional conflict often depresses team performance
Tips for Resolving Conflicts

## Slide 30: Common Sources of Conflict
Work scope
Resource assignments
Schedule
Costs
Technical opinions
Priorities of resource time
Administrative procedures
Responsibilities
Personality clashes

## Slide 31: Root Cause of Conflict
The PM has final responsibility to resolve or manage any conflict that affects project success.
For example, suppose two people are yelling at each other during a meeting. Asking them to not yell fixes the symptom, but not the root cause of the conflict, which may be a difference of opinion about an issue due to different assumptions being made by each person.

## Slide 32: Five Dysfunctions of a Team
The five dysfunctions of teams are
    Absence of trust
    Fear of conflict
    Lack of commitment
    Avoidance of accountability
    Inattention to results
*Lencioni, Patrick, “Overcoming the Five Dysfunctions of a Team,” Jossey-Bass: San Francisco, CA (2005), p. 3.

## Slide 33: General Advice on Teams
Be patient with your team
Fix the problem instead of blaming people
Establish regular, effective meetings
Allow time for teams to go through the basic team-building stages
Limit the size of work teams to three to seven members

## Slide 34: Using Software to Assist in Human Resource Management
Software can help in producing RAMS and resource histograms
Project management software includes several features related to human resource management such as
  Assigning resources
  Identifying potential resource shortages or underutilization
  Leveling resources

## Slide 35: Project Resource Management Involves Much More Than Using Software
Project managers must
  Treat people with consideration and respect
  Understand what motivates them
  Communicate carefully with them
Focus on your goal of enabling project team members to deliver their best work

## Slide 36: Chapter Summary
Project human resource management includes the processes required to make the most effective use of the people involved with a project
Main processes include
  Plan human resource management
  Acquire project team
  Develop project team
  Manage project team

## Slide 37: CAPM Sample Question
Which of the following is generally the best conflict-resolution technique in most cases?
  Avoidance
  Compromise
  Accommodation
  Collaboration

## Slide 38: CAPM Sample Question
Karl, one of your team members, is arguing with you over how to perform a specific task. At the end of a long discussion, you say “ Karl, please do me a favor and do it this way for my peace of mind.” Which conflict resolution technique are you using?
  Avoidance
  Compromise
  Accommodation
  Forcing

## Slide 39: CAPM Sample Question
Management has asked you to produce a chart that depicts the resource assignments for all the activities in the project. Which of the following charts is management referring to?
  Project Organizational Chart
  WBS
  Roles and Responsibilities Chart
  Responsibility Assignment Matrix

## Slide 40: CAPM Sample Question
Virtual Teams are a tool and technique used in which of the following processes?
  Develop Human Resource Plan
  Develop Project Team
  Acquire Project Team
  Manage Project Team